## Slide 1
EXECUTIVE RECOMMENDATION
Re-scope the transformation—keep moving, but change the focus
DEVOPS & ANALYTICS TRANSFORMATION • EXECUTIVE DISCUSSION
01
Continue safe repository moves. Shift capacity to reliable pipelines, secure exceptions, and developer experience.
WHY CHANGE COURSE?
Pipelines are the bottleneck
A repository moved to GitHub is not ready if its build, tests, outputs, or release process are unreliable.
Some workloads need a safe exception
Windows/x86 and native builds may need a restricted runner. Do not weaken controls for everyone to solve one case.
Trust matters more than speed
Use DORA data for improvement only after definitions and sources are verified—not to rank teams.
Leadership message: measure success by working, supported delivery—not repository counts alone.

## Slide 2
EXECUTION PLAN
First 90 days: understand, prove, then expand
DEVOPS & ANALYTICS TRANSFORMATION • EXECUTIVE DISCUSSION
02
DAYS 0–30 | UNDERSTAND
Name owners and inventory repositories, pipelines, dependencies, risks, artifacts, and runner needs. Agree the pilot, security baseline, measures, and rollback steps.
DAYS 31–60 | PROVE
Pilot about 20–30 representative repositories, including Windows/x86 cases. Compare old and new builds, tests, coverage, and artifacts. Collect developer feedback.
DAYS 61–90 | EXPAND SELECTIVELY
Move only workloads that pass readiness checks. Fix common friction. Review evidence and approve the next service-aligned wave.
Gate each wave on build/test parity • artifact checks • security • rollback readiness • owner approval

## Slide 3
OPERATING MODEL & GOVERNANCE
Make the secure path the easiest path to use
DEVOPS & ANALYTICS TRANSFORMATION • EXECUTIVE DISCUSSION
03
Platform team owns the paved road
Reusable workflows, migration tools, runner service, support, documentation, and reliability. Treat the platform as a product with owners and a roadmap.
Service teams own their outcomes
Code, tests, service metadata, release behavior, incident facts, and migration acceptance remain with the product teams.
SECURITY BASELINE
Least privilege
Protected branches
Secret & dependency checks
Approved actions
Production approvals
Isolated legacy runners
Exceptions are controlled—not hidden: record an owner, reason, risk, compensating protection, approver, expiry, and fix plan. Review regularly.

## Slide 4
ANALYTICS & METRIC TRUST
DORA baseline: show the evidence—and the gaps
DEVOPS & ANALYTICS TRANSFORMATION • EXECUTIVE DISCUSSION
04
164
commits
350
build records
11
incidents
2
projects
What must be validated
Commit `build_sk` versus build `build_id` linkage; whether builds represent successful production deployments; and how incidents map to deployments.
Known data warning
Only three incidents are marked deployment-caused. One incident resolution is earlier than its start. Verify source meanings before calculating a baseline.
Decision: agree definitions and sources; publish coverage and quality flags; do not rank teams on incomplete data.

## Slide 5
DECISIONS & INVESTMENT
Leadership decisions: fund the foundations and set clear gates
DEVOPS & ANALYTICS TRANSFORMATION • EXECUTIVE DISCUSSION
05
Approve now
• Named executive, platform, service, security, and analytics owners • Service-aligned migration waves and evidence-based exit gates • Staged security baseline and time-bound exception process • Azure Boards remains in one ADO organization; name integration owner • No DORA team ranking until data quality is acceptable
Invest in
• Platform product team and migration automation • Developer support, documentation, and enablement • Restricted Windows/x86 runner capacity • Security and identity expertise • Fabric data engineering and metric stewardship
DEFER FOR NOW
Mass rewrites • forced Boards migration • unsupported blanket controls • team DORA targets • autonomous production AI
DAY-90 SUCCESS
Pilots pass parity and rollback checks; owners are clear; friction is improving; analytics caveats are visible.